TELFORD & WREKIN COUNCIL
AUDIT COMMITTEE 3rd NOVEMBER 2009
HALF YEARLY PROGRESS ON THE CONSOLIDATED 2008/09 GOVERNANCE ACTION PLAN 
REPORT OF THE CORPORATE DIRECTOR RESOURCES

1 PURPOSE

1.1 For the Audit Committee to note progress against the 2008/09 consolidated Governance Action Plan.
2 RECOMMENDATIONS

2.1 That the Audit Committee notes the progress against the actions in the 2008/09 consolidated Governance Action Plan (Appendix A). 

3 SUMMARY

3.1 Under statutory regulations the Council is required to produce an Annual Governance Statement which should be signed by the Chief Executive and Leader of the Council and is included in the Annual Accounts.  

3.2 The Annual Governance Statement for 2008/09 was agreed by Cabinet and the Audit Committee in June 2008. Included as part of the statement is an action plan which identifies areas for improvement for the Council.

3.3 In addition to this action plan during 2008/09 there were governance actions identified from the work of Internal and External Audit. All these actions have been consolidated together into one action plan which CMT and the Audit Committee are responsible for monitoring.
4 PREVIOUS MINUTES

4.1
Cabinet 9th June 2009


Audit Committee 16th June 2009
5 INFORMATION ON THE CONSOLIDATED GOVERNANCE ACTION PLAN 2008/09 

5.1 The 2008/09 Annual Governance Statement (AGS) Action Plan was presented to Cabinet and the Audit Committee in June 2009 and incorporated an action plan of 13 areas for improvement.

5.2 During 2008/09 Internal Audit as part of their assurance work assessed the Councils adherence to the local Code of Good Governance. 15 recommendations were made, some of which were included in the AGS action plan.

5.3 In addition, KPMG as part of their advice sought when there was a change of Chief Executive, identified 8 governance areas for improvement. Again some of these had already been identified and included in the AGS Action Plan.
5.4 The Corporate Director Resources, as the Council’s lead governance officer requested that all governance actions from 2008/09 should be combined in one action plan. This ensures that all issues are monitored and that duplications are erased.

5.5 Attached as Appendix A is the 2008/09 consolidated governance action plan with 29 areas for improvement. The current position as at 30/09/09 of these actions is shown in the right hand side of the appendix. 

5.6 Members will note that:

a) 11 actions are complete

b) 8 actions are on target

c) 10 actions have hade revised implementations dates with the latest being 30/04/10. These are actions 1, 2, 3,4,5,9,17,22,26 and 27.

5.7 CMT and the responsible Heads of Service are confident that the revised deadlines will be achieved.

5.8 Progress at 31/03/10 will be incorporated into the 2009/10 Annual Governance Statement.

6 OTHER CONSIDERATIONS

	AREA
	COMMENTS

	Equal Opportunities
	Inclusivity is clearly in the Local Code of Good Governance

	Environmental Impact
	None



	Legal Implications
	The Accounts and Audit Regulations 2003 (as amended) place a legal obligation upon local authorities to maintain an adequate and effective system of internal audit of its accounting records and internal control in accordance with proper practices. The regulations also have a key aim of strengthening governance and accountability.  

Providing the half yearly update on the governance action plan to this committee is not a legal requirement.  However, it will help the Council to meet the requirements of the legislation as it involves a review of the action plan and helps to ensure that the plan maintains momentum and accordingly addresses the areas for improvement identified in the annual governance statement.

	Links with Corporate Priorities
	The Local Code of Good Governance should ensure improved links with the community and the delivery of appropriate corporate priorities in an open and accountable manner.

	Risks and Opportunities
	Demonstrating and operating good corporate governance mitigates some of the risks to the Council, particularly ones that may have an impact on the Council’s reputation. The opportunities and risks associated with this report have been identified and action has been put in place to ensure that they are appropriately managed.

	Financial Implications
	Good corporate governance and internal controls reduces the risk to the Council of financial loss.

	Ward Implications
	Failure of the Council to operate to the code of Good Governance could adversely affect all Wards of the Council.


7 BACKGROUND PAPERS

Local Code of Corporate Governance May 2008

CIPFA
 – Delivering Good Governance in Local Government June 2007

CIPFA’s Financial Advisory Network –ANNUAL GOVERNANCE STATEMENT - Meeting the Requirements of the Accounts and Audit Regulations 2003, incorporating the Accounts and Audit (Amendment) (England) Regulations 2006 – Rough Guide for Practitioners with effect from 2007/08

Annual Governance Statement 2008/09
Internal Audit Governance Review 2008/09

Report by Jenny Marriott, Audit & Risk Manager 383101
APPENDIX A

T&W CONSOLIDATED GOVERNANCE ACTION PLAN 2008/09
 – UPDATE TO SHOW PROGRESS AS AT 30/09/09 
	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	1.
	Corporate Business Continuity plan – 

a) review; and 

b) test.


	CD ACW and Head of P&P
	Corporate Business Continuity Management Strategy approved Jan 2009.

Priority 1 Services identified and awaiting final approval from Corporate Directors and Cabinet.

Revised Corporate Continuity Plan and Service Area Recovery Plan Template under development – delayed as awaiting approval of Priority 1 Services.

Training and Exercising to be undertaken once final approval achieved

Working closely with ICT Infrastructure Project to ensure it supports the corporate & service continuity plans.


	30/09/09

30/09/09

30/09/09

30/09/09
	Due to Corporate Restructure – Business Continuity Project was put on hold until September 2009.  In the interim, we have been responding to Swine Flu Pandemic and all Heads of Service and Business Managers have been advised to revisit existing business continuity plans to ensure they are robust enough to respond to potential staff shortages and implications on services.

Revised Priority Services to be presented for approval

Revised Corporate Continuity Plan to be presented for approval followed by appropriate training and testing of the plan
	31/12/09

31/03/10

	2.
	Revised ICT business continuity plan to be produced during 2008/09


	Head of ICT
	The proposed infrastructure designs incorporates a live data centre environment and a backup data centre environment for both corporate and education servers. These facilities are currently being developed and tested with a planned migration between June 2009 and March 2010.

The Business Continuity Plan will be revised in line with these time scales and in accordance with the review of the Corporate Business Continuity plan, which has identified priority one applications.
	30/09/09
	Progressing with implementation.
	01/12/09

	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	3.
	Ensure that ICT infrastructure projects supports the corporate & service continuity plans
	Head of ICT


	Following the review of the designs produced by the supplier it was felt that the proposed designs would not meet the requirements of the Council and all work was stopped with them. Designs were brought in house and commercial negotiations re-opened with the supplier to agree a way forward under the existing contract. This was completed in December 2009.

In –house designs have been completed and the majority of the hardware has been supplied.

A test environment will be built during April and May with Live migration of in scope applications planned between June 2009 and March 2010. 

All new server requirements will be incorporated into the new infrastructure during this period.
	30/09/09
	Progressing with implementation
	01/12/09

	4.
	Catering - Implement the outstanding areas from the internal audit review and on-going system/processes update.


	Head of BSF, Resources & Regener-ation
	An assessment is currently being made as to the benefits of implementing a cashless system as part of the catering and cleaning service review. Assuming that this review confirms that the benefits are significant then we will seek savings from within the catering annual revenue budget to offset the cost. This has the added advantage of building in ongoing sustainability. Furthermore we have also bid for funding to support the project from the DCSF. We should hear within the next month if we have been successful with this bid. In the meantime we will continue to use the system procured from PCS ensuring that a contingency plan is in place in case the system should fail. Subject to the above a business case has been prepared in line with procedures for ICT procurement and a team is ready to procure an alternative system.
	Decision on way forward by 31/05/09 and implementation by Sept 09
	Following a meeting between Internal Audit, C&YP Finance and the Head of BSF, Resources & Regeneration a number of process changes have been made to reconciliation procedures which will address outstanding points from the Internal Audit Review. In addition; though not the subject of the IA review, a new cashless system will be trailed in two schools as part of the LA Borough Towns Initiative – Sport & Learning Community (formerly Campus T&W) priority to include a single card/device for pupils use. This will be funded through a combination of grant (capital grant) and BSF resources. The trial will include linking the card to the new on line payment system offered by the revised cash receipting software.
	31/03/10



	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	5.
	Develop and agree a corporate procedure for the appointment, induction and control of consultants.


	Head of HR
	CD's have approved a policy on the Use of Consultants together with agency staff and new contract arrangements re provision of agency staff is in place with training in progress for May/June 2009 launch.

Communication of this policy and guidance on the use of consultants is still required.  
	30/09/09
	The Policy on engaging consultants has been incorporated into the new agency arrangements and policy for recruiting temporary staff.  New contract with Comensura now in place.  Policy will be reinforced in publication to all managers of the new recruitment strategy currently in final stages of consultations.
	30/11/09

	6. 
	Undertake review of the effectiveness of the system of internal audit for 2008/09 and then 2009/10.
	Audit & Risk Manager
	Agreed approach with Audit Committee 27th January 2009 based on draft guidance.

To be completed for Audit Committee 16/06/09

2009/10 review to include a repeat of the Audit Committee Effectiveness Survey
	16/06/09

31/05/10
	Complete
	

	7.
	Review operation and effectiveness of the revised Scrutiny arrangements
	Head of Finance & Audit 
	New arrangements effective from 01/01/09 and work programme has been agreed and is being delivered.

Review of effectiveness will be undertaken during 2009/10
	31/05/10
	On target
	

	8.
	Implement outstanding actions from the Ethics Survey action plan. 
	Head of Legal Services
	Consider refresher training in Human Rights or briefing through the bulletin or breakfast interactive.
	30/09/09
	This has been considered and is not required.
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	9.
	Complete review of specific areas of the Constitution
	Chief Exec, MO, Head of HR, CC Cttee and Council
	a) Personnel procedure rules – Officer Employment Procedure Rules 

b) Delegations – Personnel Board terms of reference 

c) Review Council procedure rules 


	30/09/09

30/09/09

31/01/10
	These tasks have slipped due to building in a consultation with affected officers and the committee cycle. Now scheduled for Council’s Constitution Committee in December and Council in January 2010.
	31/01/10


	10.
	Undertake a repeat of the Ethics survey. 
	Audit & Risk Manager
	Undertake survey.

Analyse results, compare to previous survey and identify any improvements/ actions required.
	31/12/09

31/03/10
	Survey to be undertaken in January 2010 to coincide with when previous survey was undertaken. The results will then be analysed and an action plan presented to the Standards Committee.
	31/01/10

Date of Stds Cttee tbc

	11.
	Undertake skills matrix work with the Audit Committee.
	Audit & Risk Manager
	Skills matrix to be agreed and completed.

Skills matrix results analysed and Committee to decide if they need/want to appoint a co-optee
	30/06/09

31/07/09
	Complete

Complete – no co-optee at present but to be kept under review. Refresher training identified.
	

	12.
	Audit Committee to present an Annual Report 08/09 to Council. 
	Chair of the Audit Committee
	Support will be provided by CD: Resources and the Audit & Risk Manager
	30/09/09
	Complete – Council 30/09/09
	

	13.
	To implement the actions from the self assessment against ISO27001.
	Heads of ICT & Information Governance
	To implement the key actions (level 1)

To implement other actions (level 2,3 & 4)
	31/07/09

31/03/10
	The Information Security Gap Analysis Status Report 2009/10 was updated 15/09/09. This reviews the Corporate Information Security Framework (CISF) to identify where gaps may exist in respect of compliance with ISO27001 Information Security Management standards and included a progress report on implementation.
	

	14.
	TOR for Standards, Audit and the other regulatory committees need to be reviewed on a regularly.
	Head of Finance & Audit and Head of Legal Services
	Internal Audit governance review 2008/09
	31/12/09
	Complete – Council 30/09/09
	

	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	15.
	Induction for Managers
	Head of Human Resources
	a) Managers should be reminded of the induction process and the corporate checklist and mandatory courses available.  This could be put in the bulletin 

or form part of Appendix A of the step by step Managers guide to the recruitment process, shown on the intranet.

b) The constitution should be linked on the HR induction page, highlighting Financial Regulations and Standing Orders 

(07/08)


	31/10/09

1/07/09


	(a)
Revised arrangements agreed by Equalities Officer Board to incorporate induction arrangements in all letters of appointment to new staff to enable them to secure induction course places direct and have their access to the check-list.  Revised letters of appointment template now in final stages of preparation.  Managers will be advised of new arrangements together with awareness of the induction check list

(b) Complete - A link has now been established (October 2009)


	31/10/09

	16.
	Communication Strategy should be in place.
	Head of PPP
	There should be a communication strategy in place. (07/08)

The strategy should be communicated to all stakeholders including hard to reach groups.


	31/12/09
	Work is progressing on this and we are on schedule to have the Communication Strategy in place by 31/12/09.

Communication to stakeholders will take place thereafter to be completed by 31/03/10.

 
	31/03/10

	17.
	Training for Members
	Chief Executive and Head of Legal Services
	Group leaders should be reminded through the member’s development programme and member appraisals that their group members should undertake the training identified for them.


	31/10/09
	The Members Development Strategy was agreed by Cabinet on 15/09/09 and this action forms part of the implementation of this.
	30/04/10

	18.
	Role descriptions for Members 
	Head of Legal Services
	Cabinet Member Resources role description should include specific lead member responsibilities for corporate governance and risk management. 

All cabinet members’ role descriptions should include general corporate governance and risk management responsibilities.
	31/08/09
	Complete
	

	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	19.
	Publication 2007/08 accounts
	Head of Finance & Audit
	The intranet should be updated with a link to the 07/08 accounts.


	31/07/09
	Complete
	

	20.
	Review of Corporate Enforcement Policy
	Head of Legal Services and Head of Finance & Audit
	The Corporate Enforcement Policy and associated prosecution policies (including the benefit prosecution policy, dated 2005 and the corporate prosecution policy, dated 2003) require updating and the latest copy shown on the intranet.

	31/12/09
	On target for Corporate Enforcement Policy

Benefit Prosecutions and Sanctions Policy will be completed by end November 2009.
	

	21.
	Review of the Partnership Protocol & Pack
	Head of Legal Services
	The partnership protocol should be reviewed and updated on a regularly agreed basis.

	31/03/10
	On target for this date.
	

	22.
	Media training
	Head of HR and Head of PPP
	Consideration should be given in making the Media Skills training course mandatory for those officers with media responsibility.

(07/08)


	31/08/09
	Work is in progress to review the Council’s Organisational Development strategy and approach in the context of future needs and requirements of the organisation.  As part of this, core competencies for managers will be assessed and training needs will then be identified and addressed.
	31/03/10

	23.
	Communication of Media protocols
	Head of PPP
	The agreed media protocols should be communicated appropriately to officers and members and should be put on the intranet.

(Town Park Review)


	31/08/09
	Complete for officers– circulated 04/09/09 and available on the intranet.

The Protocols have been presented to Cabinet Members and Group Leaders and are available on the Members Information Point.
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	24.
	Training for Managers
	Head of HR
	Disciplinary and capability training should be offered to all Business Managers

(07/08)
	31/12/09
	Training Courses are now established taking account of legal changes around discipline and grievance implemented in April 2009.  Specific Portfolio training has also taken place.


	

	25.
	HR Procedures
	Head of HR
	All HR procedures should be reviewed regularly and show a future review date 

(07/08)
	31/03/10 or part of single status
	A timescale has been established to review all workforce proceedings which include Equality Impact Assessments.  Timescales take account of the need to integrate certain policies with Single Status negotiations.
	

	26.
	Absence management
	Head of HR
	There should be standard documentation throughout the Authority to record ‘return to work’ interviews.

(07/08)
	30/09/09
	Absence Management Policy is currently being revised in consultation with Trade Unions.  New documentation is being developed within this policy around return to work.
	30/11/09

	27.
	Member/Officer relations
	Chief Exec, MO, Stds Cttee, CC Cttee, Council

Cabinet, CMT, MO
	a) Review of existing Member/Officer Protocol on member/officer relations.

b) Review the relationship between members and officers to develop a culture of trust and mutual confidence by engendering an appropriate level of collaboration, transparency and constructive challenge through external facilitation.
	30/09/09

Commenced

June09
	In light of the development with IDeA (see below) this work has been deferred awaiting the outcome of the IDeA work.

Meeting arranged between Chief Executive and Monitoring Officer and representatives from the IDeA to discuss how they can help address these issues. Postponed once at request of IDeA, due to take place on 5th October 2009.
	31/01/10
On-going



	28.
	Guidance on Gifts & Hospitality
	Chief Exec, CMT, Head of HR, MO, Audit & Risk Manager, Stds Cttee
	Review and update existing guidance
	30/09/09
	Complete - Presented to Standards Committee on 17th September 2009 and then recommended for agreement by Council on 30th September 2009
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*

	29.
	Update Officers and Members for changes made
	Audit & Risk Manager, MO, Head of HR and external trainers
	Training for officers and members on changes to governance processes and guidance including the code of conduct, the Constitution, HR policies and procedures and good governance generally.
	From Oct 09
	On going to follow on as approvals granted by Council.
	From Jan 2010


Revised Date* - where required revised dates have been inserted otherwise the original date remains valid

� CIPFA – Chartered Institute of Public Finance and Accountancy


� Consolidated from the Annual Governance Statement 2008/09 Action Plan, Internal Audit Corporate Governance Audit 2008/09 and External Audit (KPMG) 08/09


� (07/08) makes reference to the fact that the recommendation was made in  the 2007/08 Internal Audit Corporate Governance Audit and is still outstanding


� (Town Park Review) – this was a recommendation from the Town Park Review issued December 2008





6
3

