TELFORD & WREKIN COUNCIL

CABINET – 24th NOVEMBER 2009

REVIEW OF THE HOUSING ALLOCATIONS POLICY

REPORT OF THE HEAD OF OPERATIONS: (Housing, Public Protection, Substance Misuse, Mental Health & Social Inclusion)

1.0	PURPOSE

1.1	To seek Cabinet approval to the governance and project management arrangements including timeframe for reviewing the Council’s housing allocations (policy) scheme

2.0	RECOMMENDATIONS

2.1	That Cabinet endorses the approach recommended for review of the housing allocations scheme, approves proposed governance arrangements, and notes proposed project management arrangements.

3.0	SUMMARY

3.1	Although the Council is a stock transfer authority it remains a Local Housing Authority with a range of related duties and powers.

3.2	One of these duties involves having in place an approved and published housing allocations scheme for the borough. Whilst there is an approved scheme in place it has not been reviewed since the phased introduction of choice based lettings nearly three years ago.

3.3	As a consequence the existing housing allocations scheme is no longer ‘fit for purpose’. Initial work has commenced to establish a project structure, project plan, governance and reporting arrangements to enable a comprehensive review to be carried out.

3.4	The review has regard to housing needs of the borough, the Council’s current allocations scheme, the ‘ChooseYourHome’ scheme administered by WHT, government guidance and best practice, and the views of stakeholders including service users and the public at large.

3.5	It is intended to have a new housing allocations policy for the borough in place and fully operational by April 2010.

4.0	PREVIOUS MINUTES

4.1	None

5.0	TAKING FORWARD THE POLICY REVIEW

5.1 	Preliminary work has already commenced in taking forward this project (see notes at Appendix 1) however the proposed governance and project management arrangements are not yet formalised.

5.2	CAPS / Cabinet are asked to approve an approach based upon the Prinz 2 model of project management with a project board, a project steering group, nominations to specific roles, identified project resources, and an agreed timeframe for delivery of pre-agreed outcomes.

5.3	The lead Cabinet Member: A&CW (or her Cabinet Assistant) is to chair the Project Board. Proposed membership is set out in Appendix 2.

5.4	An existing project group is to be reformed into a project steering group which will be chaired by a HoS from A&CW and supported by a small number of key officers. Project resources include dedicated officer time at HoS / BM / team manager level plus consultancy advice and support through the Housing Quality Network.

5.5	The process for review and revision of the allocations policy is predicated on extensive stakeholder engagement and community consultation. This approach aims to secure genuine recognition of the key policy issues and a consensual acceptance of a new ‘fit for purpose’ allocations policy.

5.6	An outline of the proposed key stages of the review / revision process are set out below:-

- Review of existing LA housing allocations policy and the WHT administered ‘ChooseYourHome’ scheme = COMPLETED

- Gap analysis between existing policy / scheme and best practice (for example: as set out in the government guidance “fair & flexible”) = COMPLETED

- Detailed analysis of local lettings i.e. what is actually happening on the ground = WORK NEARING COMPLETION

- Stakeholder engagement / Community consultation on key issues SCHEDULED FOR MID NOV / DEC 09

- Development of and consultation on a new allocations scheme (policy) for the borough = DEC 09 / JAN 2010

- Stakeholder / community consultation on the draft scheme = JAN 2010

- Amendment (where appropriate), formal approval and publication of the new policy = FEB / MARCH 2010

- Implementation of the new policy during March & April 2010

- Post implementation policy review between January and March 2011.

5.7	The Project Board will oversee this project, with periodic update reports to the Housing and Regeneration Partnership Board. However, a new housing allocations policy will require full Council approval (during Feb / March 2010).

6.0 	INFORMATION

6.1	Equality and Diversity

6.1.1	There are no direct equality and diversity issues arising from this report.

6.1.2	Review and revision of the Council’s housing allocations policy raises fundamental equality and diversity issues. Therefore proposals set out in this report provide for EIAs to be carried out for stakeholder and community consultation processes and for the draft / final versions of a new allocations policy.

6.2	Environmental Impact

6.2.1	There are no direct environmental impacts associated with proposals set out in this report.

6.3	Legal Comment

6.3.1	A Local Housing Authority is obliged to have prepared, approved, and published a housing allocations scheme for its area under provisions of Part 6 of the Housing Act 1996 (as amended)

6.4	Links with Corporate Priorities

6.4.1	Ensuring that the Council’s housing allocations policy is ‘fit for purpose’, and is reflected in the practice of housing allocations across the borough, has a direct and indirectly positive impact for all of the Council’s key priorities.

6.5	Opportunities and Risks

6.5.1	A full risk assessment has not yet been carried out for this review process. However, the formalised project structures described in the report will have regard to ‘risk’ both in terms of delivering the project on time and within resources, and in relation to the ongoing process of allocating housing according to priority needs.

6.6	Financial Implications

6.6.1	A provision of £25k has been made from within existing revenue budgets to fund this policy review and development work.

6.6.2	There are no other direct financial implications arising from this review however a ‘fit for purpose’ housing allocations policy will help to minimise housing support costs including those relating to homelessness (i.e. housing support, temporary accommodation, loss of HB subsidy, etc).

7.0	WARD IMPLICATIONS

7.1	Proposals set out in this report have implications for households in all wards across the borough, and beyond.

Report prepared by Mike Atherton, Head of Operations (Housing, Public Protection, Substance Misuse, Mental Health & Social Inclusion) Tel: 01952 (3)81800 or email: mike.atherton@telford.gov.uk

CAB (24-11-09) – review of hsg allocations scheme / reports

Appendix 1

Review of the Housing Allocations Policy

Progress Overview

1. Governance & Project Management

The purpose of this summary report is to provide an update on progress so far and to seek approval to formal governance and project management arrangements.

Project resources (people and funding) are identified and committed. An outline project plan is in place with key milestones identified. Review and revision of the housing allocations policy will be concluded by April 2010.

Housing Quality Network are engaged to provide capacity, expertise and challenge to the policy review process.

2. Key aims / objectives of the project are to:-

Carry out a review of an existing housing allocations policy and development of a new one that:-

- meets all statutory requirements;

- accords with government guidance on housing allocations policies within the context of choice based lettings;

- supports a range of local (sub-regional, regional and national) policy objectives);

- identify and advise on options relating to potential conflicts between the aspirations of a local housing authority for the allocation of housing in its area the interests of local housing providers,

- to provide advice on arrangements for consultation with the community and key stakeholders;

- to provide advice on the benefits or otherwise of alternative models for allocating housing within a LHA area.

3. Policy Issues

Whilst not an exhaustive list the following provide examples of some of the policy issues that need to be considered when formulating revisions to the local allocations scheme:-

- achieving sustainable communities:- including achieving sustainable tenancies, creating safer neighbourhoods, and ensuring good quality living environments;

- supporting and sustaining independent living for vulnerable people;

- preventing homelessness:- including achieving key targets, and having in place effective prevention measures for a range of vulnerable people including 16 & 17 year olds;

- ensuring allocations policies actively support housing renewal and regeneration initiatives, and encourage investment to help sustain local housing areas.

The revised scheme should also have regard to a number of specific housing related issues:- overcrowding, rent arrears, domestic violence, harassment & asb, disrepair, medical & welfare needs including adaptations, local connections, etc, etc.

A new allocations policy should also support a wider range of public policy objectives including ensuring:- ready access to public transport, access to education, training & employment opportunities, access to local services including health services and treatment programmes, effective and affordable responses to climate change, achievement of affordable warmth, etc, etc.

The inter-relationship / inter-dependence of many of the issues set out above illustrate why it is important for the review process to be comprehensive and fully engaging of all stakeholder / community interests.

4. Accountability & Reporting Arrangements

Regular progress reports to be provided to:-

- Lead Cabinet Member & Cabinet Assistant

- The Project Board;

- The Housing & Regeneration Partnership Board and, where appropriate to the Health & Wellbeing Partnership Board;

- CAPS / Cabinet

Approval of full Council is required for a new housing allocations policy for the borough. The project plan anticipates that this will be in Feb / March 2010.

Appendix 2

Review of the Housing Allocations Policy

Project Board and Steering Group Membership

Project Board

1. Cllr Jacqui Seymour, Lead Cabinet Member A&CW - chair (or Cllr Rosemary Chaplin, Cabinet Assistant A&CW) 2. Paul Donohue, Interim CD: A&CW 3. Jonathan Rowe, HoS: Commissioning 4. Mike Atherton, HoS: Housing (operations) 5. Angie Astley, HoS – critical challenge for project mngt, customer service, service quality, and partnerships Support: Kathy Jones, BM: Housing & Personalisation Commissioner Ginny Hickman, BM: Housing (operations) Nicky Woodley, Administration

Project Steering group

1. Jonathan Rowe, HoS: Commissioning } joint 2. Mike Atherton, HoS: Operations } chair 3. Katherine Kynaston, Strategic Housing Manager 4. Lesley Burrows, BM: housing lead for YP 5. Rep from WHT as CYH administrator 6. Rep from CVS for independent & voluntary sector housing support 7. Kathy Jones, BM: Housing & Personalisation Commissioner 8. Ginny Hickman, BM: Housing (operations) 9. Richard Peach or Emma Cope - Finance Support: Julia Hancox, TM: Housing Commissioner Nicky Woodley, Administration Wendy Murphy, HQN