SCRUTINY LEADERSHIP BOARD

26th March 2009
Position Statement on Scrutiny Reviews

	2008-09 Programme



	Review
	Progress update
	Target date for completion of evidence gathering
	Target date for presenting  report to Cabinet
	Revised completion date for evidence gathering
	Revised date for presenting report to Cabinet
	Reason for delay

	Bus Services
	Evidence gathered/underway: Bus Users Group, Senior Citizens, YPF, Disability Forum, Arriva, Community Panel Survey, Parish Councils. 

Still to do:

Travel West Midlands, Chamber of Commerce, officers re future growth points, town centre development, Twister, network management duty, bus stations in other towns. 

Transport Service Review due to report 18th March to Review Board. The recommendations will be considered as part of the review.   
	March 09
	May 09
	April 09
	To be agreed
	Results of Community Panel survey not available until mid-late April.   
Slow down due to staffing changes and shortage in Jan/Feb.

	Procurement
	Completed: meetings with central procurement, E&R, ICT, Property & Assets, Staffordshire CC, Warwickshire CC, Mike Phillips.
To do: meetings with CYP, ACC arranged. 

Almost complete.
	February 09
	To be agreed
	March 09
	To be agreed
	

	Housing & Homelessness
	Meetings as in scope underway. Housing Associations, YMCA done.
To do:

Meetings with Bromford and the Private Landlords Association still to be arranged.

Group have also asked for meetings with planning officers.
	Early April 09
	June 09
	
	
	

	2009-10 Programme



	Review
	Scrutiny members
	Officers
	Date of scoping meeting and comments
	Scope agreed/draft attached

	Child Protection & Child Protection Plans
	Joy Francis

Louise Lomax Lynda Baker

Annette Cox

Shauket Ali 

Sue Harris
	Julia Almond

Anne Cole

Tina Knight
	To be confirmed.

Dates proposed dates were too late (April-June) so immediate dates have been requested.
	

	Cluster arrangements and locality working


	Helen Williams

Jayne Greenaway

George Ashcroft

Louise Lomax 

Keith Austin

Dennis Allen
	Richard Partington

Rachel Jones

Laura Johnson
Julia Almond
	24th March (tbc)
	

	Developing future skills for business


	Alan Mackenzie

Shaukat Ali

Keith Austin

Mel Ward

Kuldip Sahota
	Peter Smith

Corin Crane
	28th March
	

	End of life choices


	Derek White

Angela Clements

Clive Mason

Lynda Baker

Annette Cox

Dilys Davis

Val Lindley
	Paul Taylor
Christine Harrison
Jacqui Seymour

Helen Swindlehurst (PCT)
Jo Banks (PCT)
Fran Beck (PCT)

	18th March 
	

	Helping residents access benefits


	Adrian Meredith

Keith Austin 

Ute Sambrook
	Lee Higgins

Jan Evans

Andrew Meredith
	12th March
	

	Waste Management
	Roger Aveley

Louise Lomax 

Clive Mason

Adrian Williams

Annette Cox

Terry Kiernan

Maurice Viney

Mel Ward
	Dave Hanley

Sally Hall
	
	


1

