[image: image5.png]Telford & Wrekin

C OUNGC I L







                   APPENDIX B
[image: image4.png]Telford & Wrekin

C OUNGC I L









APPENDIX B


T&W CONSOLIDATED GOVERNANCE ACTION PLAN 2008/09
 – UPDATE TO SHOW PROGRESS AND EVIDENCE JANUARY 2010
	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	1.
	Corporate Business Continuity plan – 
a) review; and 
b) test.

	Head of Community Protection

	Corporate Business Continuity Management Strategy approved Jan 2009.
Priority 1 Services identified and awaiting final approval from Corporate Directors and Cabinet.
Revised Corporate Continuity Plan and Service Area Recovery Plan Template under development – delayed as awaiting approval of Priority 1 Services.
Training and Exercising to be undertaken once final approval achieved
Working closely with ICT Infrastructure Project to ensure it supports the corporate & service continuity plans.

	30/09/09
30/09/09
30/09/09
30/09/09
	Due to Corporate Restructure – Business Continuity Project was put on hold until September 2009.  In the interim, we have been responding to Swine Flu Pandemic and all Heads of Service and Business Managers have been advised to revisit existing business continuity plans to ensure they are robust enough to respond to potential staff shortages and implications on services.
Revised Priority Services to be presented for approval
Revised Corporate Continuity Plan to be presented for approval followed by appropriate training and testing of the plan
	31/12/09
31/03/10
	Organisational changes have further delayed review / revision of the corporate and service area BCPs

Most of phase 2 original changes will be completed by 31/03/10 enabling progress to be made. New BCPs to be in place by 30/06/10. 

Update report on BCP review process required by Audit Committee and scheduled for June 2010 meeting.

Corporate and service area risk assessments reviewed and updated quarterly – existing BCPs are in place to respond to identified risks. 

Plan validation and exercising to take place as soon after completion as possible.  
	30.06.10

30.06.10

Ongoing

To be scheduled


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	2.
	Revised ICT business continuity plan to be produced during 2008/09

	Head of  ICT and Procurement

	The proposed infrastructure designs incorporates a live data centre environment and a backup data centre environment for both corporate and education servers. These facilities are currently being developed and tested with a planned migration between June 2009 and March 2010.
The Business Continuity Plan will be revised in line with these time scales and in accordance with the review of the Corporate Business Continuity plan, which has identified priority one applications.

	30/09/09
	Progressing with implementation.
	01/12/09
	Progressing with implementation.

Business Continuity is planned to be updated accordingly.

Disaster Recovery sessions are being booked in with large application owners.
	Ongoing

	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	3.
	Ensure that ICT infrastructure projects supports the corporate & service continuity plans
	Head of ICT and Procurement

	Following the review of the designs produced by the supplier it was felt that the proposed designs would not meet the requirements of the Council and all work was stopped with them. Designs were brought in house and commercial negotiations re-opened with the supplier to agree a way forward under the existing contract. This was completed in December 2009.
In –house designs have been completed and the majority of the hardware has been supplied.
A test environment will be built during April and May with Live migration of in scope applications planned between June 2009 and March 2010. 
All new server requirements will be incorporated into the new infrastructure during this period.
	30/09/09
	Progressing with implementation
	01/12/09
	Progressing with implementation.

A standard virtual server template has now been created and will be signed off with security standards. All migrations and new installations onto the new platform have been designed to meet the continuity plans.
	Ongoing


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	4.
	Catering - Implement the outstanding areas from the internal audit review and on-going system/processes update.

	Head of  Property and Design

	An assessment is currently being made as to the benefits of implementing a cashless system as part of the catering and cleaning service review. Assuming that this review confirms that the benefits are significant then we will seek savings from within the catering annual revenue budget to offset the cost. This has the added advantage of building in ongoing sustainability. Furthermore we have also bid for funding to support the project from the DCSF. We should hear within the next month if we have been successful with this bid. In the meantime we will continue to use the system procured from PCS ensuring that a contingency plan is in place in case the system should fail. Subject to the above a business case has been prepared in line with procedures for ICT procurement and a team is ready to procure an alternative system.
	Decision on way forward by 31/05/09 and implementation by Sept 09
	Following a meeting between Internal Audit, C&YP Finance and the Head of BSF, Resources & Regeneration a number of process changes have been made to reconciliation procedures which will address outstanding points from the Internal Audit Review. 
In addition; though not the subject of the IA review, a new cashless system will be trailed in two schools as part of the LA Borough Towns Initiative – Sport & Learning Community (formerly Campus T&W) priority to include a single card/device for pupils use. This will be funded through a combination of grant (capital grant) and BSF resources. The trial will include linking the card to the new on line payment system offered by the revised cash receipting software.
	31.03.10
31.03.10

	A cashless system is being trialled in 4 schools.  As part of delivering the efficiencies through Catering and Cleaning there is a Project Board that takes decisions (predominantly of an operational nature) to deliver the efficiencies.  At the March 2010 board meeting a steer was given to service delivery managers to prepare a robust business case for cashless taking into account the capital allocation for 2009/10 and 2010/11.  A decision on cashless will be taken before July 2010.  Audit team have an open invitation to attend board meetings.
	30.06.10


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	5.
	Develop and agree a corporate procedure for the appointment, induction and control of consultants.

	Assistant Chief Executive

	CD's have approved a policy on the Use of Consultants together with agency staff and new contract arrangements re provision of agency staff is in place with training in progress for May/June 2009 launch.
Communication of this policy and guidance on the use of consultants is still required.  
	30/09/09
	The Policy on engaging consultants has been incorporated into the new agency arrangements and policy for recruiting temporary staff.  New contract with Comensura now in place.  Policy will be reinforced in publication to all managers of the new recruitment strategy currently in final stages of consultations.
	30/11/09
	Complete.

Policy now forms part of our requirements for managers employing consultants. Policy is published on Comensura pages of the intranet available to appointing managers.

(policy checked by audit – available on Intranet)
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	6. 
	Undertake review of the effectiveness of the system of internal audit for 2008/09 and then 2009/10.
	Audit & Risk Manager

	Agreed approach with Audit Committee 27th January 2009 based on draft guidance.
To be completed for Audit Committee 16/06/09
2009/10 review to include a repeat of the Audit Committee Effectiveness Survey
	16/06/09
31/05/10
	Complete

Complete
	
	Complete. 

A report is due to be issued to the Audit Committee on 30/03/2010 to provide members of the Audit Committee with the results of the survey completed to review the effectiveness of the Audit Committee.
	

	7.
	Review operation and effectiveness of the revised Scrutiny arrangements
	Head of Governance

	New arrangements effective from 01/01/09 and work programme has been agreed and is being delivered.
Review of effectiveness will be undertaken during 2009/10
	31/05/10
	On target
	
	On target. Report in progress and verbal report at meeting following SLB on the 25th March.
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	8.
	Implement outstanding actions from the Ethics Survey action plan. 
	Head of Governance

	Consider refresher training in Human Rights or briefing through the bulletin or breakfast interactive.
	30/09/09
	This has been considered and is not required.
	N/A
	N/A
	N/A

	9.
	Complete review of specific areas of the Constitution
	Head of Governance
	a) Personnel procedure rules – Officer Employment Procedure Rules 
b) Delegations – Personnel Board terms of reference 
c) Review Council procedure rules 


	30/09/09

30/09/09

31/01/10
	These tasks have slipped due to building in a consultation with affected officers and the committee cycle. Now scheduled for Council’s Constitution Committee in December and Council in January 2010.
	31/01/10


	Part of the full review of the Council Constitution to be completed for implementation April 2011
	a) 30.04.10
b) 30.04.10

c) April 2011


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	10.
	Undertake a repeat of the Ethics survey. 
	Audit & Risk Manager


	Undertake survey.

Analyse results, compare to previous survey and identify any improvements/ actions required.
	31/12/09

31/03/10
	Survey to be undertaken in January 2010 to coincide with when previous survey was undertaken. 
The results will then be analysed and an action plan presented to the Standards Committee.
	31/01/10

Standards 
Cttee 16/09/10
	Survey delayed due to re organisation and impending election.

Agreed with Corporate Core for issue w/c 10th May 2010 for return 28th May.  Analysis to follow and report to CMT early July 2010

	31/05/10

30/09/10

	11.
	Undertake skills matrix work with the Audit Committee.
	Audit & Risk Manager

	Skills matrix to be agreed and completed.
Skills matrix results analysed and Committee to decide if they need/want to appoint a co-optee
	30/06/09
31/07/09
	Complete
Complete – no co-optee at present but to be kept under review. Refresher training identified.

	
	Complete
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	12.
	Audit Committee to present an Annual Report 08/09 to Council. 
	Chair of the Audit Committee
David Wright
	Support will be provided by CD: Resources and the Audit & Risk Manager
	30/09/09
	Complete – Council 30/09/09
	
	Complete
	

	13.
	To implement the actions from the self assessment against ISO27001.
	Head of ICT and Procurement

	To implement the key actions (level 1)
To implement other actions (level 2,3 & 4)
	31/07/09
31/03/10
	The Information Security Gap Analysis Status Report 2009/10 was updated 15/09/09. This reviews the Corporate Information Security Framework (CISF) to identify where gaps may exist in respect of compliance with ISO27001 Information Security Management standards and included a progress report on implementation.
	
	Many ISO27001 standards have been met due to the code of connection for Government Connect. However a formal gap analysis needs to be carried out again since the changes to evaluate the gap and work required.
The implementation of any key issues identified will take place during 2010/11.
	31/03/10
31/12/10


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	14.
	TOR for Standards, Audit and the other regulatory committees need to be reviewed regularly.
	Head of Governance

	Internal Audit governance review 2008/09
	31/12/09
	Complete – Council 30/09/09
	
	Complete
Membership of Committees reviewed December 2009.
	N/A


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	15.
	Induction for Managers
	Assistant Chief Executive
	a) Managers should be reminded of the induction process and the corporate checklist and mandatory courses available.  This could be put in the bulletin 

or form part of Appendix A of the step by step Managers guide to the recruitment process, shown on the intranet.

b) The constitution should be linked on the HR induction page, highlighting Financial Regulations and Standing Orders 

(07/08)


	31/10/09

1/07/09


	(a)
Revised arrangements agreed by Equalities Officer Board to incorporate induction arrangements in all letters of appointment to new staff to enable them to secure induction course places direct and have their access to the check-list.  Revised letters of appointment template now in final stages of preparation.  Managers will be advised of new arrangements together with awareness of the induction check list

(b) Complete - A link has now been established (October 2009)


	31/10/09
	Issues now incorporated into letter of appointment. Induction lead is Debbie Germany Organisation Development & Change Manager.

The induction, learning programme will require a review as part of One Council.  This will include the induction checklist.

Priority at the moment is to create capacity within the Organisational Development and Change Management teams to do this.  All workforce development resource is being brought together.
Complete
	30/06/10


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	16.
	Communication Strategy should be in place.
	Assistant Chief Executive
	There should be a communication strategy in place. (07/08)
The strategy should be communicated to all stakeholders including hard to reach groups.

	31/12/09
	Work is progressing on this and we are on schedule to have the Communication Strategy in place by 31/12/09.
Communication to stakeholders will take place thereafter to be completed by 31/03/10. 
	31/12/09
31/03/10
	
	31/07/10
31.08.10

	17.
	Training for Members
	Head of Governance
	Group leaders should be reminded through the member’s development programme and member appraisals that their group members should undertake the training identified for them.
	31/10/09
	The Members Development Strategy was agreed by Cabinet on 15/09/09 and this action forms part of the implementation of this.
	30/04/10
	
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	18.
	Role descriptions for Members 
	Head of Governance 

	Cabinet Member Resources role description should include specific lead member responsibilities for corporate governance and risk management. 
All cabinet members’ role descriptions should include general corporate governance and risk management responsibilities.

	31/08/09
	Complete
	
	Complete
	

	19.
	Publication 2007/08 accounts
	Head of Finance 

	The intranet should be updated with a link to the 07/08 accounts.

	31/07/09
	Complete
	
	Complete
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	20.
	Review of Corporate Enforcement Policy
	Head of Governance

	The Corporate Enforcement Policy and associated prosecution policies (including the benefit prosecution policy, dated 2005 and the corporate prosecution policy, dated 2003) require updating and the latest copy shown on the intranet.

	31/12/09
	On target for Corporate Enforcement Policy
Benefit Prosecutions and Sanctions Policy will be completed by end November 2009.
Corporate Prosecution Policy not updated.

	31/12/09
30/11/09

	Complete

To Cabinet 12/01/10
Complete
Approved by Cabinet 26.01.10 to be reviewed in 3 years. Not on the Intranet as it was considered by Cabinet under closed session so access restricted.

Ongoing but should be complete by
	30/06/10


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	21.
	Review of the Partnership Protocol & Pack
	Head of Governance 

	The partnership protocol should be reviewed and updated on a regularly agreed basis.


	31/03/10
	On target for this date.
	
	Had been started but due to staff changes has been reallocated.
	30.09.10

	22.
	Media training
	Head of HR 


	Consideration should be given in making the Media Skills training course mandatory for those officers with media responsibility.

(07/08)


	31/08/09
	Work is in progress to review the Council’s Organisational Development strategy and approach in the context of future needs and requirements of the organisation.  As part of this, core competencies for managers will be assessed and training needs will then be identified and addressed.
	31/03/10
	The induction, learning programme will require a review as part of One Council.  This will include the induction checklist
As Action Number 15 above
	30.06.10


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	23.
	Communication of Media protocols
	Head of HR

	The agreed media protocols should be communicated appropriately to officers and members and should be put on the intranet.

(Town Park Review)


	31/08/09
	Complete for officers– circulated 04/09/09 and available on the intranet.

The Protocols have been presented to Cabinet Members and Group Leaders and are available on the Members Information Point.
	Complete


	Complete

A questionnaire was emailed to all Heads of Service, the Head of Human Resources (Projects) and the Assistant Chief Executive. Out of the 17 issued, 14 responses were received. The questions tested the Officers awareness and knowledge of the Authority’s media protocol. All responses received were satisfactory and confirmed officer awareness.
	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	24.
	Training for Managers
	Head of HR

	Disciplinary and capability training should be offered to all Business Managers
(07/08)
	31/12/09
	Training Courses are now established taking account of legal changes around discipline and grievance implemented in April 2009.  Specific Portfolio training has also taken place.

	
	To be included in review of development. Individual managerial briefing for specific cases part of existing processes.

Training to support these issues is continuing.  However, the way it is delivered may change as part of a future review.
	Ongoing


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	25.
	HR Procedures
	Head of HR

	All HR procedures should be reviewed regularly and show a future review date 
(07/08)
	31/03/10 or part of single status
	A timescale has been established to review all workforce proceedings which include Equality Impact Assessments.  Timescales take account of the need to integrate certain policies with Single Status negotiations.
	
	One page guidance for managers produced. 

HR policies reviewed/renegotiated include Wellbeing and Absence, Redeployment, Recruitment. Others currently part of Formal Single Status negotiations which commenced on 23rd February 2010
	Ongoing


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	26.
	Absence management
	Head of Community Protection

	There should be standard documentation throughout the Authority to record ‘return to work’ interviews.
(07/08)
	30/09/09
	Absence Management Policy is currently being revised in consultation with Trade Unions.  New documentation is being developed within this policy around return to work.
	30/11/09
	Complete

Revised Wellbeing and Attendance policy has now been agreed and formally adopted by CMT. It will come into force on 1.3.10. It includes a check list of items to cover in a return to work interview and these are reiterated on the self certification form.

(available on the Intranet)


	


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	27.
	Member/Officer relations
	Head of Governance 
	a) Review of existing Member/Officer Protocol on member/officer relations.
b) Review the relationship between members and officers to develop a culture of trust and mutual confidence by engendering an appropriate level of collaboration, transparency and constructive challenge through external facilitation.
	30/09/09
Commenced
June09
	In light of the development with IDeA (see below) this work has been deferred awaiting the outcome of the IDeA work.
Meeting arranged between Chief Executive and Monitoring Officer and representatives from the IDeA to discuss how they can help address these issues. Postponed once at request of IDeA, due to take place on 5th October 2009.
	31/01/10
On-going

	Part of the full review of the Council Constitution to be completed for implementation April 2011
	April 2011


	No.
	ACTION
	Resp.
	Original Comments 
	Date
	Comments on Position as at 30/09/09
	Revised Date*
	Position as at 
31.01.10
	Revised Date*

	28.
	Guidance on Gifts & Hospitality
	Head of Governance
	Review and update existing guidance
	30/09/09
	Complete - Presented to Standards Committee on 17th September 2009 and then recommended for agreement by Council on 30th September 2009
	
	Complete

Updated for new organisation structure from 31.03.10
	

	29.
	Update Officers and Members for changes made
	Head of Governance & Audit & Risk Manager, 

	Training for officers and members on changes to governance processes and guidance including the code of conduct, the Constitution, HR policies and procedures and good governance generally.
	From Oct 09
	On going to follow on as approvals granted by Council.
	From Jan 2010
	Ongoing during 2010. Governance, Risk, Audit and Fraud training update for members March 2010. 
Further training for members will be arranged once the constitution changes have been agreed
	April 2011


Revised Date* - where required revised dates have been inserted otherwise the original date remains valid[image: image1.png]


[image: image2.png]


[image: image3.png]









� Consolidated from the Annual Governance Statement 2008/09 Action Plan, Internal Audit Corporate Governance Audit 2008/09 and External Audit (KPMG) 08/09


� (07/08) makes reference to the fact that the recommendation was made in  the 2007/08 Internal Audit Corporate Governance Audit and is still outstanding


� (Town Park Review) – this was a recommendation from the Town Park Review issued December 2008





8
24

[image: image4.png][image: image5.png]