TELFORD & WREKIN COUNCIL

CABINET – 23rd FEBRUARY 2010
2009/10 FINANCIAL MONITORING
REPORT OF THE HEAD OF FINANCE
1.0 PURPOSE

To provide Members with the latest financial monitoring information for 2009/10 relating to: the revenue budget and capital programme, income collection, treasury management and the payment of supplier invoices.  
2.0
RECOMMENDATIONS

Members are asked to note:
2.1 The further rise in the Children & Families service overspend.
2.2 Projected spend overall is still within budget but very little contingency remains to cover the last quarter’s activities
2.3 The performance on Treasury Management and against targets for income and the payment of supplier invoices

2.4 To approve the new capital allocations, capital virements, and re-phasing detailed in Appendix III, which following Cabinet will go forward to Full Council for formal approval.
3.0 SUMMARY
3.1 Revenue
Overall revenue spend is currently projecting to be within budget by year end but the cost of Looked After Children has increased again by over £0.5m since the last report with an overspend of £1.816m currently being projected (which is after taking into account the £1.4m additional funding previously agreed).  The overspend on Specialist Education has reduced and now stands at £0.525m.  Some one-off funds have been identified which assist the overall position, however these have reduced from previous projections and the underlying cost is a key pressure that is being closely monitored.  Costs relating to winter maintenance are starting to emerge and the projected overspend currently stands at £0.240m - this may increase if the period of exceptionally cold weather continues.  Increased benefits have arisen from concessionary travel, £0.130m, and treasury where a further £0.100m is reported.
3.2 Capital
The 2009/10 approved capital programme is £69.3m; to date 40% spend has taken place.  The capital programme relies on a significant amount of capital receipts as part of its funding and the current monitoring highlights some delays and reductions against assumed sale prices starting to emerge.
3.3 Income Monitoring

Council tax collection and Adult Social Care sales ledger are ahead of target; NNDR and General Sales Ledger are behind target which is a reflection of the impact of the recession.  It should also be noted that targets were adjusted to take into account the economic conditions.
3.4 Invoice Payment Performance

The target for 2009/10 is to pay 95% of invoices within 20 days; overall year to date performance is below this at 93%.  September and November were particularly poor months and Service Delivery Units are asked to review processes so that the target is met by year end.  
4.0 PREVIOUS MINUTES
4.1
05/03/09 – Full Council, Service & Financial Planning Strategy

21/07/09 – Cabinet, Financial Performance Report


27/10/09 – Cabinet, 2009/10 Financial Monitoring Report


12/01/10 – Cabinet, 2009/10 Financial Monitoring Report

5.0 2009/10 REVENUE BUDGET
5.1 Spend is currently projected to be within budget at year end but very little contingency remains to cover the final few months activities.  Detailed variations for each Service Delivery Unit are shown in Appendix II.  The table below summarises the overall position by Service Delivery Unit:
	 
	Projected Year End Variation - £

	Service Delivery Unit
	Corporate
	Service
	Total

	
	
	
	

	Safeguarding & Corporate Parenting
	0
	1,816,000
	1,816,000

	Learning & Achievement
	0
	663,232
	663,232

	Regeneration & Housing
	0
	(76,086)
	(76,086)

	CYP One Off Balances/Other Variances
	0
	(1,349,146)
	(1,349,146)

	Property & Design
	244,000
	429,000
	673,000

	Economic Development
	0
	50,000
	50,000

	Environmental Services
	423,000
	(149,000)
	274,000

	Planning & Transport
	354,000
	(180,000)
	174,000

	Adult Social Care (Delivery)
	0
	292,000
	292,000

	Adult Social Care (Commissioning)
	0
	(192,000)
	(192,000)

	ASC Other Variances
	0
	(159,000)
	(159,000)

	Customer Services
	(1,784)
	(138,321)
	(140,105)

	Governance
	(75,176)
	(115,753)
	(190,929)

	ICT & Procurement
	0
	(43,482)
	(43,482)

	Finance
	28,805
	3,853
	32,658

	Core Services
	121,407
	9,236
	130,643

	Council Wide
	(864,964)
	
	(864,964)

	
	
	
	

	Total
	229,288
	860,533
	1,089,821

	
	
	
	

	Call on the Budgeted Contingency
	
	
	(1,089,821)

	
	
	
	

	Projected Year End Position
	 
	 
	0


5.2 The projected service variations fall to Services to cover from their balances or offsetting areas of underspend under their control.
5.3
The larger projected variances (those over £100k) are highlighted separately below, while full detail on all variances over £50k are shown in Appendix II.
	Key
	
	
	

	£0 to £100k
	
	
	Underspend

	£101+to £250k
	
	
	Overspend

	£251+to £500k
	
	
	

	over £500k 

	
	
	

	Variances

	Service Delivery Unit
	Projected Variation £m

[change]

	Safeguarding & Corporate Parenting
The current projected overspend stands at £1.816m which is after the £1.4m virements from pay/general inflation benefits and treasury previously approved.  This is an increase of £0.547m since the last report.  
£1.0m of the overspend relates to Looked After Children.  The current number of children in care is 270 which reflects around 33 additional placements above the average throughout last year.  External Foster Care placements have increased by 33 since January 2009 – the average cost of an annual  placement of this type being around £40k.
£0.816m of the overspend relates to Social Work and the additional cost of agency staff due to ongoing vacancy levels, increased numbers of assessments and care proceedings.

This position may change dependent on future movement in placements and placement types, and with the impact of the placements strategy.  Monitoring of external and leaving care placements.  Costs are subject to a robust monitoring system.  The scale of the overspend is not out of line with that being faced by a number of other authorities reflecting a national pressure.

	+1.816
[Increased Overspend]


	
[image: image1]

	Learning & Achievement

Specialist Education – Pressure continues with the projected overspend based on the latest information available; additional costs relating to a further 2 children placed from October are now included.

	+0.525
[Reduced Overspend]


	

	One off Balances and Other Variations across all CYP Service Delivery Units – A total benefit of £1.349m has been identified towards the Service Delivery Unit overspends identified above.  This is a combination of £0.965m flexible use of grant income and £0.384m from other underspends.

	-1.349
[Reduced benefit]


	
[image: image2]

	Property & Design

Asset & Property Management – projected shortfall in PIP rental income due to a high level of void properties and other PIP costs; an impact of the recession.  
The service is actively trying to increase occupancy levels
Use of one-off balances to meet rental shortfall


	+0.918
[Increased Overspend]

-0.247
[increased benefit]
	

	Planning & Transport

Planning Fees – shortfall in planning fees due to a downturn in the economy.

Use of previous years trading surplus and vacancy management.
Public Inquiries – inquiry into the planning application for opencast mining in Lawley.  There is a further inquiry highlighted relating to Granville Incinerator with legal costs of £0.074m falling in 2009/10; costs associated with any appeal will fall in 2010/11.


	+0.300

[unchanged]
-0.200

[unchanged]

+0.354

[Increased overspend]
	

	Landfill costs – benefits from increased recycling and diversion from landfill.


	-0.280

[Increased benefit]
	
[image: image3]

	Environmental Services

Concessionary Travel – benefit of £0.100m due to changes in demography (over and above the service review)
Street Lighting energy costs - £0.129m overspend 


	-0.100

[Increased benefit]

+0.129

[Reduced overspend]
	


	Adult Social Care (Delivery)

Adults with Learning Disabilities – increased cost of care packages due to an increase in demand as clients move from Children’s to Adult Services.  This is partly offset from Assessment & Care Management underspends, due to vacant posts which are included in the Staff Savings below.
Physical and Sensory Disability – this has decreased by £0.035m since last reported due to vacant staff positions and movement of funded support from nursing to home care reducing overall costs
Housing Needs – the cost of initiatives to reduce the number of people in temporary accommodation; reducing the usage and cost of B&B has a positive impact on the amount of benefit subsidy the authority loses (which is flagged as a council wide benefit in Appendix II)


	+0.128
[Increased overspend]

+0.100
[Reduced overspend]

+0.082
[Reduced overspend]
	
[image: image4]

	Older People Services – a benefit of £0.208m; a reduction on previously reported figures as the effects of the winter period is now starting to be seen in increasing costs..
Charging Policy – provision towards meeting costs arising from the revised charging policy
 
	-0.208
[Reduced benefit]


+0.250

[No Change]
	

	Adult Social Care Commissioning

Supporting People – being used to offset pressures across Adult Social Care purchasing, detailed above.

	-0.192
[Reduced benefit]


	
[image: image5]

	Various Staff savings – underspends arising from vacancies in Social Worker posts, core support posts and part year effect of restructure carried out earlier in 2009/10.  This has reduced slightly on previously reported figures as management strategies are resulting in Social worker posts being filled.

	-0.159
[Reduced benefit]
	

	ICT & Procurement
A trading benefit of £0.113m for ICT is projected which relates mainly to vacant posts which are part of the 2010/11 budget savings proposals.

	-0.113
[increased benefit]
	

	Customer & Leisure Services

Telford Ice Rink – shortfall of income due to the impact of the recession and a fall of 12% in attendance compared to last year.
Leisure Centres – net position across other leisure centres, including £0.043m benefit from Wellington Aspirations.

	+0.116

-0.207

	

	Core Services

Business Efficiency Team – the unfunded element of the business efficiency team.


	+0.109

[Reduced overspend]


	

	Treasury – benefits from restructuring undertaken earlier in the year, the impact of cash flow and the changed regulations for calculating MRP have given rise to a projected underspend of £1.0m for 2009/10, after the £0.400m virement to Children & Families.  This is after  meeting the additional revenue costs of the £6m BTI/Roads investment and the anticipated lower returns from Fund Mangers.  More detail is included in para 8. Below.

	-1.000
[increased benefit]
	
[image: image6]

	Coroner – additional costs relating to inquests

	+0.141
[increased overspend]
	


5.4
An additional £1.400m support has been provided to the Children and Families budget in 2009/10 (through virements from Treasury and general inflation/pay allowances).  This is in line with the investment being proposed for placements in the 2010/11 budget strategy.
6.0 CONTINGENCIES
6.1 The 2009/10 budget includes combined contingencies of £1.596m which are set aside to meet any unforeseen expenditure but potentially little remains to cover the final quarter unless current projections improve:

	
	£m

	General Revenue Contingency
	0.596

	Additional Contingency – one off only
	1.000

	
	1.596

	2009/10 approved spend:
Princess Royal Hospital Campaign – one-off

One-Off investment to provide additional support and preventative work in Children & Families services in 2009/10.  Ongoing investment is included in the 2010/11 budget strategy.
Rapid Response Team – One-Off investment to fund pilot, to accelerate repairs to roads.

	0.040
0.150

0.235

	Total of 2009/10 Approvals
	0.425

	Balance required to offset the current revenue position
	1.089

	Balance available in the contingency to meet any unforeseen expenditure that may arise in the remainder of the year.
	0.082


7.0
2009/10 CAPITAL PROGRAMME


The capital programme for 2009/10 totals £69.263m.  Expenditure at the time of compiling this report was £27.99m and is shown by priority theme in the table below
	 
	2009/10
	2009/10
	%
	2009/10

	 Priority Area
	Approved 
	Expenditure
	
	Projected

	 
	Budget
	To Date
	
	Expenditure

	 
	£m
	£m
	
	£m

	 
	 
	
	
	

	Adult Care & Support
	1.504
	0.209
	13.90
	0.878

	Active Lifestyles – Leisure & Culture
	1.353
	0.196
	14.48
	0.250

	Housing, Regeneration & Prosperity
	25.059
	5.669
	22.62
	15.758

	Children & Young People
	19.290
	11.427
	59.24
	18.948

	Environment & Rural Areas
	12.303
	6.625
	53.85
	11.731

	Community Protection & Cohesion
	2.810
	1.311
	46.65
	2.466

	An Efficient Community Focussed Council
	6.944
	2.551
	36.74
	5.502

	Total
	69.263
	27.988
	40.41
	55.533


7.1 There are a number of new allocations, virements and slippage reported which will require formal approval at Full Council.  These are shown in Appendix III.
7.2 Capital receipts form a significant element of the funding of the Council’s capital programme - Around £80m capital receipts are anticipated in 2009/10 and future years.  Failure to achieve, or delays to, the receipts has potentially very significant financial implications for the council and the position is being closely monitored.  Key issues highlighted relating to the current programme are:

	i
	Railfreight – Two £425k receipts due in 2009/10 have both been delayed one until 2010/11 and the other until 2011/12 with short-term borrowing costs of £0.018m in the current year, rising to £0.060m in 2010/11; a further receipt due in 2010/11 is also showing a £400k anticipated shortfall, and alternative receipts are being sought to cover this.



	ii
	Old Park School - £3.650m receipt due in 2011/12 is now deferred to  2013/14 resulting in short-term borrowing costs of £0.082m in 2011/12, rising to £310k in 2012/13 (this has been included in the 2010/11 budget strategy)



	iii
	Uncommited future receipts of £1.5 have been identified that will help to cover this shortfall when realised. 


8.0 TREASURY

8.1
The Council’s treasury management position at the beginning of the year and the current position is as follows: -

	
	
	31 March 2009
	31 Dec 2009

	
	
	Principal
	Principal

	
	
	£m
	£m

	Fixed Rate Borrowing
	
	125.024
	108.024

	Variable Rate Borrowing
	
	   64.099
	   13.631

	Total Debt
	
	189.123
	121.655

	
	
	
	

	Investments - in-house
	
	84.507
	46.850

	       - with external managers
	
	   58.397
	  39.463

	Total Investments
	
	142.904
	86.313

	Net Indebtedness
	
	46.219
	35.342

	
	
	
	


8.2
Activities since 1st April 2009


Base Rate has been held at 0.5% since the start of the year and inflation had fallen, but has recently started to increase and RPIX for December is 3.8%.


The overall aim of Treasury Management is to achieve the maximum return with minimum risk.  In this current period of lower interest rates the strategy is to reduce investments and borrowing as the opportunity arises.

Since the beginning of the year the Council has repaid £17m of PWLB debt, this consisted of 2 loans, one that was in discount for £213,378 and one that incurred a premia of £190,671. Under regulations discounts are taken to the revenue account over 10 years and premium are charged over 25 years, benefiting the revenue account by £14,000 each year for the first 10 years, coupled with this the loans were running at 4.25% and 4.5% and our temporary borrowing rates have been considerably lower than this. This short term saving will mainly benefit 2009/10 but will also have benefits in later years.  We have recently taken 2 further loans to replace PWLB falling out in 2010/11 at the current favourable rates.
We have had a number of investments mature during the first part of the year and these have been used to repay temporary borrowing. The Council also carried out a review of Fund Managers during July and it was decided to reduce the number of fund managers from 3 to 2. At 31st October the whole of the investment managed by the third fund manager had been returned to the Council. This has been used to reduce temporary borrowing.  The intention is to withdraw a further £10m from fund managers by the end of February; this will be used to reduce borrowing.
Overall our net indebtedness has fallen from £46.2m to £35.3m since the start of the year. This is consistent with the cashflow benefits the Council experiences each year with income from Council Tax and NDR more than offsetting revenue spend in the first half of the year. A significant amount of spend is geared to the second half of the year with the main part of this being capital spending.

There have been a number of reviews published since the Icelandic Banking crisis, including those from the Audit Commission and Cipfa. The Council has reviewed its policies and procedures in the light of these reports and we have worked closely with our Treasury Advisors Sector during this time with whom we regularly monitor the Council’s investment portfolio.  
The Council has one investment which since entering into has fallen below our credit rating criteria.  As previously reported, the counterparty is guaranteed by the Belgium government and we see little risk in continuing to hold the investment.  This position will continue to be regularly monitored.

8.3 A projected benefit of £1.400m is reported for 2009/10.  This is a combination of benefits from debt restructuring undertaken earlier in the year; changes to the way MRP is calculated (the amount the Council has to charge for the cost of borrowing); and cash flow net of underperformance of investment income, including Fund Manager returns.

8.4 
Treasury projections include payment of interest on internal balances which due to the very low interest rates will be considerably less than in previous years – this mainly affects Section 106 monies and school balances.
8.5
The Audit Committee have amended their terms of reference to enable then to take an active role in monitoring the Council’s treasury management activities and training has been and will be offered to members of the Committee to enable then to fulfil this role.

9.0
CORPORATE INCOME MONITORING

9.1 The Council’s budget includes significant income streams which are regularly monitored to ensure they are on track.  The three main areas are Council Tax, NNDR (business rates) and Sales Ledger income.  Current monitoring information on first year collection rates is provided below.  
The Council continues to pursue outstanding debt beyond the first year vigorously, until all possible recovery avenues have been exhausted, but also prudently provides for bad debts in its accounts.  The economic conditions have been considered when setting the targets for 2009/10.
	Council Tax
	2008/09 Outturn
	97.7%

	
	2009/10 Target 
	97.2%

	
	2009 Debit
	£57.7m


First Year performance to the end of December is:
	
	Month End Target
	Month End Actual
	Dec
2008

Actual
	Variance

	The percentage of council tax collected
	85.77
	85.77%
	85.99%
	On target


	NNDR
	2008/09 Outturn
	98.3%

	
	2009/10 Target 
	97.8%

	
	2009 Debit
	£64.8m



First Year performance to the end of December is:

	
	Month End Target
	Month End Actual
	Dec
2008

Actual
	Variance

	The percentage of NNDR collected
	87.81%
	87.36%
	87.84%
	-0.45% behind target


NNDR collection is 0.45% behind the target for December 2009 and 0.48% behind the actual in December 2008; although behind target the position has improved this month.

Sales Ledger Income

Recovery processes for other income due to the Council varies between income billed by Social Services, around £24m p.a., and the rest, which is also around £24m p.a.

Adult Social Care
	Outstanding Debt
	Target

%
	Dec 2009
	

	
	
	£’000
	%
	

	2 – 6 months
	0.9%
	218
	0.9
	At target

	7 – 12 months
	0.6%
	70
	0.3
	Inside target

	> 12 months
	1.1%
	97
	0.4
	Inside target

	Total
	2.6%
	385
	1.6
	Inside target



Other Council Services

Performance to the end of December is:
	Percentage of Outstanding Sales Ledger Debt:
	Target
	Month End Actual
	Variance

	2 – 6 months
	2.5%
	2.12%
	0.38% inside target

	6-12 months
	1.1%
	1.71%
	0.61% outside target

	Over 12 months
	1.3%
	1.51%
	0.21% outside target

	
	
	
	

	Total
	4.9%
	5.34%
	0.44% outside target


The position has significantly improved over the last few months with a particular focus on the 2-6 month category.
10.0
PAYMENT OF INVOICES

10.1
In 2009/10 a target has been set to pay 95% of invoices within 20 days  of receipt.  Paying invoices promptly is one of the ways the Council can help suppliers as it benefits their cash flow.  The payments system was also changed in February 2009 so that all invoices input are paid immediately.
10.2 Performance for November showed the Council overall achieving 93% which is behind the 95% target set.  Service Delivery Units have been reminded to ensure invoices are processed promptly to ensure the target is met during 2009/10.
11.0 OTHER CONSIDERATIONS
Equality & Diversity
There are no implications directly arising from this report.  

Environmental Impact
There are no implications directly arising from this report

Legal Comment


Regular financial monitoring forms part of the assurance for strong financial management.  Section 28 of the Local Government Act 2003 makes it a statutory duty for Local Authorities to monitor their income and expenditure against budget, and to take action if overspends or shortfalls in income emerge.
Links with Corporate Priorities

           Good financial monitoring and the efficiency agenda form part of building a Modern, Effective Council
Opportunities & Risks

The opportunities and risks associated with the report have been identified and assessed.  Arrangements will be put in place to manage the risks and maximise the opportunities that have been identified.

Financial Implications

The financial implications are fully detailed within the report.  

Ward Implications

District Wide Implications

12.0    BACKGROUND PAPERS
2009/10 Budget Strategy / Financial Ledger reports

Report Prepared by: 

Ken Clarke, Head of Finance – 01952 383100; 

Pauline Harris, Corporate Finance Manager - 01952 383701










5

