
TELFORD & WREKIN COUNCIL
AUDIT COMMITTEE 20th SEPTEMBER 2011
INTERNAL AUDIT QUARTER 1 2011/12 UPDATE REPORT
REPORT OF THE AUDIT & ASSURANCE MANAGER
1 PURPOSE

1.1 To update members on the work of Internal Audit during quarter one – April – June 2011.
2 RECOMMENDATIONS

2.1 That members of the Audit Committee note the information in the quarter one update report.
3 SUMMARY

3.1 The Audit Committee receives a quarterly update of the work of Internal Audit. This report includes the update report for quarter one – April to June 2011.
4 PREVIOUS MINUTES

4.1
Audit Committee 22nd March 2011 – Internal Audit Annual Plan and Strategy 2011/12

5 INTERNAL AUDIT – QUARTER ONE UPDATE (APRIL - JUNE 2011)

5.1 
The report provides information on the work of Internal Audit during April to the end of June 2011 and provides an update on the progress of previous audit reports issued (April 2009 to March 2011).
5.2 Internal Audit activity during this period has focussed on the completion of the audits set out in the Internal Audit Plan including starting areas of work for the external auditor. Some work has been undertaken during the quarter to support the go-live of the new financial management system.
5.3 
The following appendices are attached to the report:

i) Appendix A – List of final reports issued in quarter one with our grading – red, amber, yellow or green. This report also includes budgeted time, actual time and percentage variance. 
ii) Appendix B – List of all work undertaken for quarter one of 1 day or more.

iii) Appendix C - Previous graded reports from April 2009 to March 2011 with their current status. (Members should note that green reports have now been excluded from this report).
5.4 Appendix A shows that 13 final reports were issued in quarter 1. 
5.5 The audit areas shown in the table below were over their allocated time by more than +/- 5% for the reasons highlighted below:

	Area
	Variance (> +/- 5%)
	Reason

	Community Centres
	+15%
	Community Centres had not been audited for a long time and all centres were looked at as part of this review.


	Redundancy payments
	+13%
	Sample size for testing increased to ensure that the process was robust

	Newport Pool
	+64%
	Some additional time due to it being the first audit visit for newly promoted member of staff.


	Children’s statutory complaints 
	+100%
	New audit area required detailed research into legislation.
Training needed to use IT system

Complicated processes to audit



	Putting People First – Mainstreaming & Developing Personalisation
	-14%
	Self assessment was used to reduce the audit time as completed by the service area 

	St Matthews Primary School
	-13%
	Schools well prepared, limited queries and revised working practices have reduced the time required.

	Newdale Primary
	-9%
	

	Millbrook Primary school
	-10%
	


Most of the positive variances have been where additional work has been undertaken but there have been several negative variances resulting from the revised working practices and restructure.  Further time allocations during 2011/12 will be reviewed based on this information. 

5.6 Areas of more than 10 days in Appendix B are explained below:

a) Advice and Guidance including organisational change – increased requests due to organisational and systems/process changes

b) AGS assurance and certification – verification of information provided by Service Delivery Units in support of the Annual Governance Statement for 2010/11 
c) Community centres – included in table 5.5 above

d) Council tax/NNDR – these are fundamental audits undertaken each year.

e) ICT Procurement – the time allocation for this review is 25 days so further information will be included in future report to members.
f) Review of costs and work for CMT – this was unplanned work to undertake a costs review for Service and Financial Planning Group to assist in the identification of savings and further work for service areas.
g) The Place, Oakengates – this review has taken longer than planned because in addition to the standard programme there were recommendations from previous reports to be followed up. Further information will be provided in future reports to members.
5.7 Due to our limited resources we have reviewed our working practices with regard to follow ups. All amber and red reports are followed up by an audit visit and testing to ensure that recommendations have been implemented as agreed by management. If reports are graded as yellow we issue a follow up template to the Manager and request that this is completed and returned to Audit services with the required evidence. We do not continue to chase managers for a response. They are advised that the grading of the report will not change until they have provided the appropriate follow up evidence.

5.8 From Appendix C the position on the original red/amber reports that remain amber or require highlighting to members are as follows (see also paragraph 5.9 below):

	No
	Area Audited 
	Original grade
	Revised grade
	Current position/comments

	1.
	ICT Security of Data Transfer 

	Amber
	Yellow
	Information sharing review completed and draft report is currently in the process of being agreed. Actions have been taken such as information sharing agreement for the Council and major partners.


	2.
	Car Parking and enforcement
	Amber
	
	Follow up in progress of being agreed but delayed due to restructuring.



	3.
	External FMSis – Adams Grammar
	Amber
	Amber
	Follow up carried out. Status remains unchanged. Work still in progress at school but due to become an academy September 2011.

	4.
	Review of Financial Records in a Care Home
	Amber
	Yellow
	Recommendations still outstanding. Recommendations responsibility of management to implement, audit will not be undertaking further follow up as per revised arrangements.

	5.
	Arthog Complaint
	Amber
	Yellow
	Follow up carried out and moved to yellow. 

	6.
	Protocol system review
	Amber
	Yellow
	Follow up received but some recommendations still outstanding. Further follow up to be completed in quarter 2.

	7.
	ICT Change management
	Amber
	Yellow
	Follow up of all outstanding ICT recommendations is undertaken on a monthly basis. Some recommendations in relation to this audit remain outstanding.

	8.
	Children’s Placement Costs 2010-11
	Amber
	
	Follow up in progress. Update will appear in future report to members


5.9 The table shows that there are three reports that have remained amber.  Due to restructuring the Car Parking and enforcement follow up responses have been delayed. For the others we are working with the appropriate managers to ensure improvements can be reported in the next update report.

5.10 There were no amber reports issued in quarter 1. All other areas previously audited are either improving or the follow ups are in progress or planned. Internal Audit is confident and it has been assured by management that controls have and will continue to improve in all areas where recommendations have been made.  There are no other issues to bring to the attention of the Committee at this time. 
6
OTHER CONSIDERATIONS
	AREA
	COMMENTS

	Equal Opportunities
	All members of Audit & Assurance have attended equal opportunities/ diversity training. If any such issues arose during an audit or risk review they would be notified to the appropriate manager.

	Environmental Impact
	Such issues would be notified to the appropriate manager during or immediately following the audit review.


	Legal Implications
	The Accounts and Audit (England) Regulations 2011 states that the Council shall maintain an adequate and effective system of internal audit of its accounting records and of its system of internal control in accordance with proper practices in relation to internal control.  There is also a requirement to give consideration to CIPFA’s Code of Practice for Internal Audit in Local Government.  Undertaking the audits as set out in the report and providing an update to this Committee contributes towards meeting these requirements.

In the event that an audit reveals an issue which requires a recommendation concerning a legal matter this can also be referred to the Council’s Legal Services Team for further advice and assistance.  

	Links with Corporate Priorities
	The audit plan is linked to corporate priorities via the risk management process.  Where high risks are identified then Audit Services undertakes work on a more regular basis.

	Risks and Opportunities
	The role of internal audit includes a review of the controls in place to manage the risks within service areas.  The reports produced assist the Council in improving systems and controls (reducing risks) and therefore the delivery of services and achievement of objectives.

	Financial Implications
	There are no financial implications arising from this report. 
Where recommendations are made by Audit Services, if possible, cost implications are identified.

	Ward Implications
	Internal Audit is responsible for the internal audit of all the Council’s activities and at all Council locations and therefore operates within all Council Wards. 


7
BACKGROUND PAPERS

Annual Audit Plan 2011/12
Report by Jenny Marriott, Audit & Assurance Manager 383101 
APPENDIX A

FINAL REPORTS ISSUED QUARTER ONE – APRIL  – JUNE 2011
	Audit Area
	Opinion
	Follow Up Due 
	Days allocated
	Days Taken
	Variance

	St Matthews Primary School
	Green
	n/a
	7.5
	6.5
	-13%

	Information Governance
	Yellow
	Oct11
	*
	
	

	Newdale Primary
	Green


	n/a
	7.5
	6.8
	-9%

	Community Centres
	Yellow
	December 2011
	10.5
	12.1
	+15%

	Absence Management
	Yellow
	June 2012
	*
	
	

	Millbrook Primary school
	Yellow
	September 2011
	8.5
	7.6
	-10%

	Redundancy payments
	Yellow
	December 2011
	4.5
	5.1
	+13%

	Putting People First – Mainstreaming & Developing Personalisation
	Yellow
	April 2012
	7
	6
	-14%

	Taxi Licensing compliance review 2011
	Yellow
	December 2011
	**
	4.7
	**

	Newport Pool
	Yellow
	December 2011
	5
	8.2
	+64%

	Children’s Statutory

Complaints 
	Yellow
	December 2011
	7.5
	15
	+100%

	Payment Card Industry Standard
	Yellow
	December 2011
	*
	
	

	Software Licensing
	Yellow
	December 2011
	*
	
	


* = Work undertaken by Audit Partners Deloittes under ICT Audit Contract or general agreement with Haines Watts

** = Consultancy / investigation work taken from contingency

APPENDIX B

QUARTER 1 - AREAS WHERE WORK UNDERTAKEN HAS BEEN FOR MORE THAN 1 DAY

	Area Reviewed
	Days

	  Abacus system review
	9

	  Adult Complaint work
	4

	  Advice/Consultancy + organisational change
	11

	  AGS assurance & certification
	11

	  Benchmarking
	1

	  Cash Collection - general
	2

	  Catering - Systems Development
	1

	  Community Centres
	12

	  Council Tax / NNDR including ward data checks
	12

	  Direct Payments review
	3

	  Education liaison/dev groups
	2

	  Elections
	4

	  Email & Internet Filtering
	3

	  External Audit Liaison Meetings
	3

	  FMS System development
	4

	  Follow ups 
	6

	  Fraud & Compliance Checks
	3

	  Fraudulent Credit Cards
	2

	  Geographical Information System
	1

	  ICT Procurement
	16

	  Information assurance
	1

	  Madeley Infants School
	1

	  Mash Media
	2

	  Meals on Wheels
	5

	  National Fraud Initiative
	9

	  Newdale Primary School
	7

	  Newport Junior School
	6

	  Newport Pool
	8

	  NGP Grant
	1

	  P2.net system
	2

	  Performance Indicators
	3

	  Play builder grants
	2

	  Putting People First
	4

	  Redundancy Payments process
	1

	  Review of Costs and follow up work for CMT
	16

	  Risk management
	9

	  Safeguarding/Protocol Information Security Review
	3

	  School Funds
	3

	  Social Care Service Improvement
	8

	  St Matthews School
	7

	  The Place
	18

	  Transparency Agenda
	3

	  Travel Link
	1

	  William Reynolds Junior School
	1


[image: image1.png]



PAGE  
6

